FOR HIGH-VALUE INVESTORS  •  TRUSTEE-SECURED  •  TERM BASED ROI

Urbco Investors App

Project Plan — High-Investment Edition

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Frontend complete. All sides confirmed.
Backend to build in 1 week. Testing included from day one.

Large capital • Fixed-term returns • Quarterly dividends inside the app • Trustee-held until milestones

| Item | Detail |
| --- | --- |
| Repository | github.com/TaiwoAjibola/test-investors-urbco (branch: main) |
| Version | v1.1 — High-Investment Edition • September 2026 |
| Prepared for | CEO & Development Team |
| Frontend Status | ✅ Complete — 19 routes/sides confirmed (see Appendix A) |
| Backend Sprint | ⏱ 7 Days Only — All UI sides frozen; backend + integration + testing |
| Deployment | Vercel (FRA1) — auto-deploy from main, output .next |

How to use:  Review together in a 45-min session (cover 1-week plan + high-investment positioning). CEO signs off on trustee milestones; Dev confirms backend day plan. Comments directly in Google Docs after import. View → Show outline for navigation.

# 1  Executive Summary

Urbco is now positioned for high-value investors who deploy large capital — ₦10M to ₦100M+ per asset — and earn term-based ROI (up to 22.5% p.a.). Instead of fragmented retail tickets, investors make a single large allocation that is held by independent trustees until construction milestones are verified. Quarterly dividends are paid directly to the in-app wallet, and the portfolio inside the app shows live valuation, allocation, and term progress. At the end of the fixed term, capital plus returns are settled.

Frontend is complete and all sides/pages are confirmed (landing, auth, marketplace, asset detail, checkout, portfolio, dividends, wallet, referrals, notifications, profile/KYC, settings, dashboard). This plan covers only the backend build — a 7-day sprint to deliver APIs, trustee milestone logic, and full integration — with testing built in every day, not after.

Outcome after 1 week: investor can allocate millions → see “Held by Trustees” → receive quarterly dividends in wallet → track ROI in portfolio → receive capital+ROI at term — fully live on Vercel production.

# 2  Objectives & Success Criteria

## Objectives (high-investment focus)

Serve high-value investors: single large allocation (₦10M–₦100M+) per asset, not instalments, with fixed-term ROI and quarterly dividends paid inside the app.

Make trustee security tangible: every investment shows “Held by Trustees → Released on Milestone” and the wallet/portfolio reflect dividend flows.

Keep frontend frozen; deliver backend in 7 days — auth/KYC, properties/marketplace, investments/trustee, wallet/dividends, portfolio/notifications — wired to the confirmed UI sides.

Ship to Vercel prod with 99.5% uptime, LCP <2s, zero critical security issues, and E2E critical paths green.

## Success criteria after 7 days

| Area | Target |
| --- | --- |
| Large allocation flow | Allocate ₦10M+ → checkout → portfolio shows holding + term ROI in <3 min |
| Trustee visibility | All investments display Held by Trustees / Released on Milestone; wallet shows dividend source |
| Dividends in app | Quarterly dividends land in Wallet, visible in Portfolio & Dividends history |
| Quality | Coverage >70% (unit+integration), all P0/P1 bugs closed, E2E large-ticket scenarios green |
| Performance & security | Lighthouse ≥90, LCP <2s; npm audit 0 high/critical; headers verified |

# 3  Stakeholders & Roles

| Role | Person | Responsibilities | Decides |
| --- | --- | --- | --- |
| CEO | CEO | High-investment positioning, trustee milestone definitions, copy & go/no-go | Scope, launch |
| Backend Dev(s) | Dev Team | 7-day backend build, API contracts, integration, deploy | Technical approach |
| QA / Tester | Dev + QA | Test plan daily, manual + automated, bug triage | Quality gate |
| Design | Design | Already delivered — 19 sides confirmed; minor copy tweaks only | UX frozen |

Note: Frontend is frozen — no UI redesign during the 7-day sprint. Only wiring and backend logic. All sides are confirmed.

# 4  Scope

## In scope — MVP (high-investment, 7-day backend)

Landing (confirmed): hero “Deploy Large Capital. Earn Term-Based ROI.” — badge For High-Value Investors, stats Avg Ticket ₦15M+ / 22.5% term ROI, How High-Value Capital Grows, dividends-in-app features, calculator ₦10M–₦100M, testimonials from ₦25M–₦50M investors.

Auth + KYC: signup, login, OTP, forgot-password, profile/KYC document upload — JWT auth backend.

Marketplace & Asset Detail: live opportunities for large tickets, funding progress, trustee milestone markers.

Checkout: single large allocation (no instalments), trustee hold, success + receipt.

Portfolio + Dividends + Wallet + Referrals + Notifications + Settings: all confirmed sides — wire to backend; dividends quarterly to wallet.

Dashboard: growth chart, allocation donut, upcoming dividends — live data.

## Out of scope — Phase 2

Fractional retail instalments (3/6/12 months) — not needed for high-value term model (full allocation only).

Secondary market trading between investors.

Dedicated trustee/admin verification dashboard (use manual milestone confirmation in sprint; automate later).

Native mobile apps — web is primary.

# 5  Technical Architecture

| Layer | Choice / Detail |
| --- | --- |
| Frontend (DONE) | Next.js 16.2.6 App Router, React 19.2.4, TS 5.8, Tailwind 4, Radix, Framer, Recharts, Zustand — 19 routes confirmed |
| Backend to build (7 days) | Node.js (or Python) API, PostgreSQL, Prisma/TypeORM, JWT, file storage (S3/R2), email/OTP provider |
| API Contract | NEXT_PUBLIC_API_URL=https://api.urbcoinvest.com; REST; types in src/types/index.ts, validation in src/lib/validations.ts |
| Trustee flow (backend) | investments table: status Held by Trustees → milestone verification → Released; dividends table: quarterly cron |
| Infra | Vercel FRA1, framework nextjs, build npm run build, output .next; GitHub main auto-deploys |
| Security | Headers in vercel.json (nosniff, DENY, XSS-block, strict-origin, Permissions-Policy); env flags ENABLE_* |

### Confirmed sides (frontend frozen)

19 routes: / (landing), /auth/login, /auth/signup, /auth/otp-verify, /auth/forgot-password, /marketplace (Own-a-Fraction), /assets/[id], /checkout/[id], /checkout/success, /dashboard, /portfolio, /dividends, /wallet, /referrals, /notifications, /profile, /profile/kyc, /settings, /about, /services. All responsive, with skeletons/empty states — no UI changes in backend sprint.

# 6  1-Week Backend Sprint — Day-by-Day

Frontend ready. All sides confirmed and frozen. Only backend + integration + testing remain. Daily demo at 5pm with Vercel preview.

| Day | Focus | Build | Demo / Exit |
| --- | --- | --- | --- |
| Day 1 | Auth & KYC | Signup/login/OTP/JWT, profile, document upload (ID, selfie, proof), /profile/kyc — wire auth/* pages | Auth E2E passes (OTP → profile) |
| Day 2 | Properties & Marketplace | Assets CRUD, funding progress %, milestones, search/filters (location/type/status) — wire marketplace + assets/[id] | Marketplace & asset detail against real API |
| Day 3 | Investments & Trustee | Allocate ₦10M–₦100M+ (single lump), status Held by Trustees, milestone verify → release — wire checkout | Large allocation E2E → wallet shows held |
| Day 4 | Wallet, Dividends & Referrals | Quarterly dividends to wallet, transactions, balance, referrals — wire wallet/dividends/referrals | Dividends land in wallet on schedule |
| Day 5 | Portfolio, Dashboard & Notifications | Holdings, live valuation, growth/alloc charts, notifications, settings — wire portfolio/dashboard | Portfolio shows term ROI live |
| Day 6 | Integration | Replace src/data/mockData.ts with live API across ALL confirmed sides; payments, email/OTP, storage; error/loading states | Full click-through all 19 sides, no mocks |
| Day 7 | Testing & Launch | Unit+integration+E2E (Playwright), security (audit+headers), Lighthouse, UAT with CEO + 2 high-value personas, prod deploy | Prod smoke test pass, rollback drill, launch |

## Milestones in 7 days

| Day | Deliverable | Owner | Exit |
| --- | --- | --- | --- |
| D1 | Auth + KYC | Dev | Login/signup/OTP E2E green |
| D2 | Marketplace Live | Dev | Real assets, funding progress accurate |
| D3 | Trustee Flow | Dev + CEO | CEO confirms milestone triggers (e.g., foundation, roofing) |
| D4 | Dividends in App | Dev | Wallet & dividends E2E passes |
| D5 | Portfolio Live | Dev | Term ROI visible in portfolio/dashboard |
| D6 | All Sides Wired | Dev | No mockData; full integration across 19 sides |
| D7 | Production Launch | All | Vercel prod verified, UAT signed |

Note: If trustee API needs change, keep mock fallback + feature flag — frontend stays frozen, so backend can keep pace.

# 7  Development Workflow (Frontend Frozen)

### Branching

main is production (Vercel auto-deploys). Backend work in feat/backend-* → PR → 1 approval → squash merge. No direct push to main. Frontend pages not edited except API wiring.

### CI Gates

Every PR must pass npm run build + lint. Add Vitest + Playwright to CI — block merge on failure. npm audit on dependency PRs.

### Contracts First

Define API types early (Day 1) matching src/types/index.ts — so frontend can wire with mocks while backend builds.

### Daily Review

15-min standup + 30-min demo at 5pm with Vercel preview link. CEO gives feedback same day on trustee copy / dividend display.

# 8  Testing Strategy — Built In Every Day

Testing is not Day 7 only. Each day lands with tests. CEO sees test report at each 5pm demo.

| Level | Tool | What | When |
| --- | --- | --- | --- |
| Unit | Vitest + Testing Library | utils (formatCurrency/formatPercent, ROI calc), stores | Daily, >70% lines |
| Integration | Vitest + MSW | api.ts, KYC, marketplace filters, dividends logic | Daily |
| E2E | Playwright | Large allocation (₦10M+) → trustee hold → wallet dividends → term ROI | D3–D7 green |
| Visual | Chromatic/manual | Hero ₦10M–₦100M slider, white logo h-10 transparent, no box | D6 no regression |
| Security | npm audit + headers | deps, vercel.json headers | 0 high/critical |
| Performance | Lighthouse CI | Landing + marketplace | Perf ≥90, LCP <2s, CLS <0.1 |

## Critical E2E scenarios (must pass before launch)

1. Allocate ₦10M+ → OTP → checkout success → portfolio shows Held by Trustees + term ROI.

2. Quarterly dividend lands in Wallet → appears in Portfolio & Dividends history.

3. At term: capital + 22.5% p.a. settled → portfolio reflects closed position.

4. KYC document upload → status in profile/KYC page updates.

5. Landing high-investment copy correct: Deploy Large Capital, ₦10M–₦100M slider, Avg Ticket ₦15M+.

"test": "vitest",   "test:e2e": "playwright test",   "test:ci": "vitest run --coverage"

UAT (CEO + 2 high-value personas): run checklist in GitHub Issue on D7. Blocks production promotion. Covers large allocation, trustee copy, dividend amounts, portfolio math, mobile experience.

## Environments & Deployment

| Env | How | Purpose |
| --- | --- | --- |
| Local | npm run dev | Dev machine |
| Preview | Vercel PR Preview (auto per PR) | Share with CEO daily |
| Production | Vercel main (auto) | FRA1, env NEXT_PUBLIC_API_URL, ENABLE_* |

If copy looks stale, check Vercel dashboard SHA matches main HEAD. Instant rollback available.

# 9  Risks & Mitigations (1-Week Context)

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Scope creep to Phase 1 retail instalments | Medium | Keep full allocation only — no 3/6/12 month plans in high-value MVP |
| Trustee milestone ambiguity | High | CEO to confirm triggers D1 (foundation/roofing/handover) — block Day 3 without it |
| Frontend freeze broken | Medium | No edits to landing/marketplace except API wiring; copy frozen at this plan |
| Logo/box regression | Low | White logo urbco-logo-white.svg (transparent, h-10) on dark; purple on light — verified D6 |
| Compressed testing | High | Tests written alongside code daily (not D7); E2E runs on CI every PR |

# 10  Communication & Review Cadence

Daily 5pm Demo (15 min): Dev shows Vercel preview; CEO signs off same day — prevents overnight rework.

Async: GitHub Issues for bugs/decisions, PR comments for code. No long email threads.

Decision log: pinned Issue ‘Decisions’ — records scope/copy changes with date + owner.

# 11  Budget & Resources (CEO Planning)

Frontend cost is sunk (complete). 1-week cost = backend dev time + Vercel/API hosting + domain. Testing stack (Vitest/Playwright) is open-source. KYC provider fees only if moving beyond light KYC.

| Resource | Estimate | Note |
| --- | --- | --- |
| Backend Developer | 1 FTE × 7 days | Core build + integration |
| QA / UAT | ~0.3 FTE in week | E2E + CEO walkthrough D6–D7 |
| Vercel + API hosting | Existing | Preview + prod |
| Design | Frozen | No cost — 19 sides already confirmed |

# 12  Next Steps — For Joint Review (This Week)

ACTION REQUIRED — Confirm at kickoff TODAY:

1.  CEO confirms trustee milestone triggers (what releases funds — e.g., foundation completed, roofing, handover). Needed for Day 3.

2.  CEO approves high-investment scope: ₦10M–₦100M+ full allocation only (no instalments in MVP) and confirmed 19 sides are frozen.

3.  Dev creates GitHub Project board with D1–D7 cards and adds CI (build + lint + test) to block bad merges — today.

4.  Add Vitest + Playwright and land first 5 tests (auth, allocate, dividends) — due end of Day 1.

5.  Schedule daily 5pm demos + D7 launch window (calendar invite + Vercel preview link).

### Sign-off

| Role | Signature |  |
| --- | --- | --- |
| CEO | _________________________ | Date: __________ |
| Backend Lead | _________________________ | Date: __________ |

# Appendix A  Confirmed Sides — Frontend Frozen

19 routes/pages reviewed and confirmed — no UI changes during 7-day backend sprint, only API wiring:

Landing / — hero Deploy Large Capital, stats Avg Ticket ₦15M+, calculator ₦10M–₦100M, dividends-in-app features, high-ticket testimonials.

/auth/login, /auth/signup, /auth/otp-verify, /auth/forgot-password — light KYC onboarding.

/marketplace (Own-a-Fraction) — grid/list, search, filters; /assets/[id] — gallery, funding, ROI, trustee markers.

/checkout/[id] + /checkout/success — single large allocation, receipt.

/dashboard, /portfolio, /dividends, /wallet, /referrals, /notifications, /profile, /profile/kyc, /settings — all confirmed.

Types src/types/index.ts, stores src/stores/appStore.ts, utils src/lib/utils.ts, config, validations — ready for backend types.

Logos: public/urbco-logo.svg (purple, light bg) + public/urbco-logo-white.svg (white, transparent, h-10, dark bg).

Infra: vercel.json (build npm run build, regions [fra1], security headers), .env.example flags ENABLE_*.

Import into Google Docs: Upload this .docx to drive.google.com → Open with Google Docs. Headings appear in outline (View → Show outline).